## Sheet1
Work Package 1 : September
Game |  | Engine |  | Scenario Editor
Assets | Concept Art | Input | Mouse Input System | System Setup | Django Application
| Character Style Specification |  | Keyboard Input System |  | Angular JS Application
| 10 Character Designs |  | Controller Input System | Conversation Editor | Conversation Editor
| 4 Sets of 3D Chair and Table Components | Shaders | Base Shader Class
| 4 Sets of Table Components | Transform Hierarcy | Matrix Stack
| 4 Sets of Lamp Components | File Loading and Processing | Texture Loader
Player Controls | Generic First Person Player Controller | Node System | Base Node Class
Procedural Furniture Generation | Mock-Up and Prototype |  | Node Updatable
Narrative Content | Rough Draft of Story |  | Node Renderable
Character Interaction - Conversations | Generic Conversation System | SWEET | Engine Initializer and Destructor
UI | Escape Menu | OpenGL: Window | OpenGL Window
Room Generation | Map Generator | OpenGL: Context | OpenGL Context
Scenario Handler
Character Animation | Humanoid Character Rig
Audio Visual Ties - Visual Distortion | Prototype Screen Space Shaders
Loading Scenarios | Individual Scenario Loader
•
Work Package 2 : October
Game |  | Engine |  | Scenario Editor
Assets | 20 Character Designs | Input | Generic Control Mapping System | Room Specification | Room Specification System
| 4 Sets of Character Components | UI Layout and Optimization | Generic Layout System | Character Editor | Base Character States Editor
| 1 Song | Transform Hierarcy | Transform Class |  | Base Character Builder
| 10 Props | Mesh Interface | Vertex Buffer Object |  | Joint Positioning System
| 4 Toilets |  | Vertex Array Object | Components | Component Uploader
| 4 Sinks |  | Index Buffer Object
| 4 Bath/Showers | File Loading and Processing | OBJ File Loader and Parser
| 4 Potted Plants |  | JSON File Loader and Parser
Player Controls | Polished Player Controller | Audio | Basic Audio Playback System
Item Generation | Generic Cupcake Specification System | Text | Font Loading System
Procedural Character Generation | Random Character Generator | Lighting Model | Lighting Model Shader
Procedural Furniture Generation | Chair and Table Generator |  | Omni-Light
Character Interaction - Conversations | Conversation Iterator |  | Lambert Material
UI | UI Mockups for Menu and Inventory | FBOs Frame Buffer | Generic Frame Buffer Class
Alpha Sorting | Alpha Sorting Mechanism | Cameras | Perspective Camera
Room Generation | Item, Character, Prop, Furniture Population System |  | Orthographic Camera
Loading Scenarios | Generic Multiple Scenario Loader | Animation: Easing | Port of Penner Easing Equations
| JSon to C++ Loader | Node System | Node Loadable
| Scenario Management System |  | Node Resource
Node Shadable
|  | Entity | Child Transform System
|  | Scenario | Node Content
|  | Particle System | Base Particle System
|  | Game | Scene Manager
|  | SWEET | Time Step
|  | Sprite | Base Sprite Class
Sprite Sheet Animation
|  | Z-Fighting | Polygon Offset Shader
|  | Shader Component System | Text Shader Component
Alpha Shader Component
Depth Shader Component
HSV Shader COmponent
Model View Projection Shader Component
Phong Shader Component
Text Shader Component
Tint Shader Component
Blinn Shader Component
Indexed Texture Shader Component
Shadow Shader Component
Diffuse Shader Component
Normals Shader Component
Component Shader System
|  | Physics: Generic Physics Node | Generic Physics Node
|  | Physics: 2D - Box2D | Node Box2D Body
|  | Physics: 3D - Bullet | Node Bullet Body
|  | Physics: Collision and Raycasting | 2D Collision
3D Collision
Raycasting
|  | Entity: Scene | Camera Management System
|  | Entity: Mesh Entity | Base Mesh Entity
Mesh Rendering System
•
Work Package 3 : November
Game |  | Engine |  | Scenario Editor
Assets | 20 Sets of Character Designs | Shaders | SSAO Shader | Room Specification | Room Content Specification System
| 4 Sets of Bed Components | Audio | Positional Audio System | Components | Component Tagging System
| 4 Sets of Dresser/Drawers |  | Streaming Audio System |  | Component Browsing System
| 4 Sets of Cupboards/Bookshelves | Text | Optimized Text Rendering System | File Syncing | File Syncing System
| 10 Props |  | Text Layout System
| 2 Song | Lighting Model | Directional Light
| Footstep Sound Effects |  | Blinn Material
| Collision Sound Effects |  | Phong Material
| Cheering Sound Effects | FBOs Frame Buffer | Render Surface
| Booing Sound Effects | Node System | Node Child
Item Generation | Generic Drink Specification System |  | Node Transform
Prop Generation | Twist Deformer | Scenario | Node Content
Procedural Character Generation | Basic Procedural Character Generator |  | Trigger Class
Procedural Furniture Generation | Bathroom and Kitchen Furniture Generator |  | Asset Class
AI | Basic Behavior System |  | Character Class
Character Interaction | Thought Bubble Display |  | Dialogue Class
| Friendship Point System |  | Conversation Class
Character Interaction - Following | Basic Follow Mechanic |  | Scenario Iterator
Character Interaction - Yelling | Functional Prototype of Yelling Game | Animation: IK | Joint Class
Item Interaction | Item User Interface |  | Bone Class
| Status Effects |  | Animation Rig Class
UI | Context Sensitive Cursor System | Animation: Tweens and Keyframes | Tweened Animation System
| Basic Menu UI | Entity: Scene | Light Management System
Basic Inventory UI
Room Generation | Door Travel System
File Sharing/Network | Base File Syncing System
Character Animation | Prototype Animations
Inventory System | Complete Inventory Sytem
Loading Scenarios | Complete Multiple Scenario Loader
Rendering | Item State Rendering System
Status and Stats Effects | Status and Stats Management System
Saves | Local Save System
•
Work Package 4 : December
Game |  | Engine |  | Scenario Editor
Assets | 10 Sets of Character Designs | UI Layout and Optimization | Linear and Horizontal Layout System
4 Sets of Trees
4 Sets of Couch Components
4 Sets of Wall Hangings
10 Props
Prop Generation | Flare Deformer
Procedural Character Generation | Final Procedural Character Generator
Procedural Furniture Generation | Bed Generator
Dresser and Drawers Generator
Cupboard and Bookshelf Generator
AI | Final Behavior System
Narrative Content | Second Draft of Script
Character Interaction - Conversations | Final Conversation System
Character Interaction - Following | Finalized Follow Mechanic
Character Interaction - Yelling | Finalized Yelling Mechanic
UI | Final Menu UI
Final Inventory UI
Basic Yelling Mechanic UI
Basic Conversation UI
Character Animation | Finalized Character Animations
Scripted Scenes | Scripted Scene System
Inventory System | Item Interaction System
Item Tracker
Coolness Points | Coolness Points System
•
Work Package 5 : January
Game |  | Engine |  | Scenario Editor
Assets | 15 Character Designs |  |  | UI and Styling | Finalized UI
15 Redesigned Characters to Fit Component Model
3D Model of Inter-Dimensional Room
2 Song
Drinking Sound Effects
Eating Sound Effects
Talking Sound Effects
Interface Sound Effects
Sci-fi Sound Effects
Procedural Furniture Generation | Foliage Procedural Generator
Couch Procedural Generator
Wall Hanging Procedural Generator
Narrative Content | Finalized Intro
UI | Finalized Yelling Mechanic UI
Finalized Conversation UI
File Sharing/Network | Online Accounts
Emotes | Basic Emotes
Saves | Online Cloud Saves
Scripted Scenes | Scripted Intro Scene
•
Work Package 6 : February
Game |  | Engine |  | Scenario Editor
Assets | 20 Character Designs
20 Redesigned Characters to Fit Component Model
Portrait Omar Room Components
4 Sets of Fridge Components
4 Sets of Stove Components
4 Sets of Hanging Light Fixture Components
Hedge Maze
10 props
Prop Specific Sound Effects
2 Songs
Procedural Furniture Generation | Fridge Generator
Stove Generator
Hanging Light Generator
Narrative Content | Finalized Main Story Line for Middle Act
Finalized Main Story Line for Final Act
Rough Side Quests
Audio Visual Ties - Visual Distortion | Visual Distortion Shaders
Loading Screen | Loading Screen Animation
Emotes | Finalized Emotes
Menu Options | Variable Screen Resolution Mechanic
Scripted Scenes | Scripted Middle Act Story Sequences
Promotional Website | Promotional Website
•
Work Package 7 : March
Game |  | Engine |  | Scenario Editor
Assets | 20 Character Designs
20 Redesigned Characters to Fit Component Model
4 Sets of Fire Place Components
4 Sets of Trunk Components
4 Sets of Wash and Dryer Components
10 props
Prop Specific Sound Effects
2 Songs
Procedural Furniture Generation | Fire Place Generator
Trunk Generator
Washer Dryer Generator
Narrative Content | Finalized Side Quest Story Lines
Menu Options | Categorized Volume Modifier
Screen Selector
Audio | Procedural Audio Generator
•
Work Package 8
Game |  | Engine |  | Scenario Editor
Assets | Game Posters
Presenation Props (Dixie Cups, Balloons)
Presentation Slides
Posters Giving Context to Development
Team T-Shirts
3D Print Outs mold
Candy in Heart Shapes
Narrative Content | Additional Dialog